PHASE 1 v2

Sprint Plan, Developer Split, and Runbook

Six-week execution plan, owner split, rituals, release loop, and founder sales runbook.

| Document ID | P1V2-08 |
| --- | --- |
| Version | 2.0 - Enhanced after Phase 1 review |
| Prepared for | Internal founding team |
| Target niche | Independent restaurants, cafes, and small restaurant groups |
| Primary backend language | Golang for backend services and workers; Next.js/TypeScript for web UI |

Core principle: validate demand through personalized demos before building a full SaaS platform.

# 1. Developer Responsibility Split

Figure 1. Two-developer ownership model.

| Developer | Owns | Secondary support |
| --- | --- | --- |
| Developer 1 | Frontend, Go core API, restaurant/menu/demo/reservation, dashboards, deployment. | Analytics UI, client onboarding, QA. |
| Developer 2 | Email automation, AI receptionist, content automation, Go workers, provider adapters, analytics events. | Backend contracts, dashboard integration, QA. |

# 2. Six-Week Execution Plan

| Week | Theme | Developer 1 | Developer 2 | Exit criteria |
| --- | --- | --- | --- | --- |
| 1 | Foundation | Repo, Go API, Postgres, auth skeleton, restaurant CRUD. | Provider adapter interfaces, campaign model, AI flow design, analytics model. | Local/staging foundation works; restaurant lead can be created. |
| 2 | Demo core | Menu CRUD, demo payload generator, first template, public slug route. | Email templates, preview flow, tracking events. | Admin can generate and preview personalized demo. |
| 3 | Outreach and reservations | Reservation API/form/dashboard. | Email sending, click tracking, follow-up sequence. | Tracked email opens/clicks and reservation submissions work in staging. |
| 4 | AI receptionist pilot | Reservation dashboard polish, owner dashboard shell. | Inbound voice sandbox, intent router, reservation from call, call summaries. | Scripted AI call can create pending reservation. |
| 5 | Content and onboarding | Client onboarding checklist, live-site conversion flow. | Content generation job/API/UI, content safety review, analytics dashboard. | Demo can become client record; content draft works. |
| 6 | QA and sales readiness | Mobile polish, deployment hardening, release checklist. | AI/content evals, email compliance checklist, demo campaign reporting. | Founders can confidently show MVP to real restaurants. |

# 3. Weekly Rituals

Monday planning: select tickets that directly support demo generation, outreach, reservations, or sales readiness.

Daily 15-minute sync: blockers, decisions, and integration points only.

Wednesday integration check: merge and test frontend/backend/provider flows; avoid end-of-week integration surprises.

Friday demo: show working software, not slides; record gaps and next-week priorities.

End-of-week retro: decide what to cut, simplify, or defer based on validation goals.

# 4. Definition of Done

Acceptance criteria are met and tested locally.

Feature works in staging with staging credentials.

Input validation and error handling are implemented.

User-facing UI handles empty/loading/error states.

Structured logs include request/job IDs without leaking sensitive data.

Critical paths have basic tests or documented smoke tests.

Feature is included in the release checklist if client-facing.

Documentation and runbook are updated.

# 5. Founder Sales Runbook

Build a list of 50 high-fit restaurants using the lead score model.

Create and manually review 10 demo sites before sending any email.

Send in small batches of 5-10 emails to protect reputation and learn from responses.

Prioritize leads with clicks, CTA interactions, or replies.

Use sales calls to validate whether website, reservations, AI receptionist, or content is the strongest pain.

Offer a paid pilot or setup package immediately when pain is clear.

Update product roadmap only from repeated sales evidence, not isolated requests.

# 6. Release Loop

Figure 2. Phase 1 release loop with explicit approval and measurement gates.